## Sheet1
TASK | YEAR 1
| J | F | M | A | M | J | J | A | S | O | N | D
Receive approval from Catholic Charities
Obtain funding from various sources
Seek out gardeners, volunteers, and other team members
Collect data on what food people like to eat and what grows best
Purchase seeds
Grow seeds into seedlings
Build hoop house and raised beds
Put up fence
Rototill plot
Make signs & put in plot to inspire others to grow and volunteer
Gleaning
Advertise the giving garden/food bank plot in various media
Bed preparation
Planting
General maintenance of garden
Pest Management
Set up tents and tables for produce stand
Harvest produce
Weigh produce and track donations
Clean and bag produce
Sell produce at stand
Donate/Deliver produce to food bank
Host health fairs, gardening workshops, and nutrition education
Analyze the outcome data
Prep garden for next year's season
Conduct evaluation on successes, failures and plan for next year